## Task Register
Task ID | Description | Category | Priority | Owner | Est. Hours | Cost (USD) | Dependency | Status | Due Date
GD-001 | Write LLM contamination disclosure (LDS-001, 1 page) | Governance | P0 | Research Lead | 4h | $0 | None | [ ] Pending | Day 3
GD-002 | Write case selection bias disclosure (CSDS-001, 1 page) | Governance | P0 | Research Lead | 3h | $0 | None | [ ] Pending | Day 3
GD-003 | Write evidence boundary statement (EBS-001, 1 page) | Governance | P0 | Research Lead | 4h | $0 | None | [ ] Pending | Day 3
GD-004 | Add GD-001/002/003 disclosures to all 10 case reports | Governance | P0 | Research Lead | 6h | $0 | GD-001/002/003 | [ ] Pending | Day 5
GD-005 | Add verubecestat PC-011 contextualisation note | Governance | P0 | Research Lead | 2h | $0 | None | [ ] Pending | Day 3
GD-006 | Freeze Pharma Constitution v1 (written note, dated) | Governance | P0 | CEO | 1h | $0 | None | [ ] Pending | Day 1
GD-007 | Pre-specify Cases 11–20 selection criteria (written, dated) | Governance | P1 | Research Lead | 6h | $0 | None | [ ] Pending | Day 14
GD-008 | Write Evidence Manifests for all 10 cases (retroactive) | Governance | P1 | Research Lead | 40h | $0 | GD-003 | [ ] Pending | Day 21
GD-009 | Assign case IDs and version numbers to all 10 case reports | Governance | P1 | Research Lead | 2h | $0 | None | [ ] Pending | Day 7
LC-001 | Engage legal counsel — scope: PAT, DPA, IP, liability, NDA | Legal | P0 | CEO | 2h | $5–12K | None | [ ] Pending | Day 1
LC-002 | Pilot agreement template PAT-001 (4–6 pages) | Legal | P0 | Legal | 16h | Included | LC-001 | [ ] Pending | Day 20
LC-003 | Data Processing Agreement template DPAT-001 (3–4 pages) | Legal | P0 | Legal | 12h | $3–8K | LC-001 | [ ] Pending | Day 20
LC-004 | IP ownership clause for council outputs | Legal | P1 | Legal | 4h | Included | LC-001 | [ ] Pending | Day 20
LC-005 | Liability limitation clause (council is advisory only) | Legal | P1 | Legal | 4h | Included | LC-001 | [ ] Pending | Day 20
LC-006 | NDA template for pilot discussions | Legal | P1 | Legal | 4h | $1–3K | LC-001 | [ ] Pending | Day 20
LC-007 | Professional indemnity insurance (£1M minimum) | Legal | P2 | CEO | 4h | $2–8K/yr | None | [ ] Pending | Day 28
LC-008 | Review regulatory disclaimer language for all external docs | Legal | P1 | Legal | 4h | Included | LC-001 | [ ] Pending | Day 22
MP-001 | Create GitHub repository (agenthinkmesh/pharma-council-v1) | Methodology | P0 | Engineering | 4h | $0 | None | [ ] Pending | Day 7
MP-002 | Write README.md (methodology overview, limitations, citation) | Methodology | P0 | Research Lead | 6h | $0 | MP-001 | [ ] Pending | Day 10
MP-003 | Publish Pharma Constitution v1 (constitution-v1.md) | Methodology | P0 | Research Lead | 2h | $0 | MP-001 | [ ] Pending | Day 10
MP-004 | Publish persona definitions (personas.md) | Methodology | P0 | Research Lead | 3h | $0 | MP-001 | [ ] Pending | Day 10
MP-005 | Publish LIMITATIONS.md (all 7 limitations, full text) | Methodology | P0 | Research Lead | 3h | $0 | MP-001 | [ ] Pending | Day 10
MP-006 | Publish torcetrapib case summary — public version | Methodology | P0 | Research Lead | 4h | $0 | GD-001, MP-001 | [ ] Pending | Day 13
MP-007 | Publish evidence manifest schema (JSON schema) | Methodology | P1 | Research Lead | 3h | $0 | MP-001 | [ ] Pending | Day 13
MP-008 | Publish OVS scoring rubric (methodology/scoring.md) | Methodology | P1 | Research Lead | 4h | $0 | MP-001 | [ ] Pending | Day 13
MP-009 | Write CITATION.cff file | Methodology | P1 | Engineering | 1h | $0 | MP-001 | [ ] Pending | Day 13
MP-010 | Write LICENSE file (CC BY 4.0 for methodology) | Methodology | P1 | Engineering | 1h | $0 | MP-001 | [ ] Pending | Day 7
MP-011 | Reproducibility test: re-run torcetrapib with same inputs | Methodology | P2 | Research Lead | 8h | $0 | MP-001 | [ ] Pending | Day 28
CA-001 | Write methodology one-pager (1 page, external, PDF) | Commercial | P0 | CEO | 6h | $0–2K | GD-001 | [ ] Pending | Day 18
CA-002 | Write CRO partnership one-pager (1 page, external, PDF) | Commercial | P0 | CEO | 4h | $0–2K | CA-001 | [ ] Pending | Day 18
CA-003 | Redesign torcetrapib IPR for external presentation (6 pages) | Commercial | P1 | Research Lead | 8h | $0 | GD-001 | [ ] Pending | Day 21
CA-004 | Create demo slide deck (6 slides, torcetrapib) | Commercial | P1 | CEO | 8h | $0–2K | CA-001 | [ ] Pending | Day 21
CA-005 | Write sofosbuvir case summary (1 page, PDF) | Commercial | P1 | Research Lead | 4h | $0 | None | [ ] Pending | Day 21
CA-006 | Write pilot proposal template (1 page, PDF) | Commercial | P1 | CEO | 4h | $0 | LC-002 | [ ] Pending | Day 22
CA-007 | Write validation library summary extract (2 pages, PDF) | Commercial | P1 | Research Lead | 4h | $0 | None | [ ] Pending | Day 18
CA-008 | Personalise Email 1 for all 5 Day-29 targets | Commercial | P0 | CEO | 3h | $0 | CA-001 | [ ] Pending | Day 28
CA-009 | Populate CRM workbook with Day-29 contacts | Commercial | P0 | CEO | 2h | $0 | None | [ ] Pending | Day 28
CA-010 | Torcetrapib flagship one-pager (visual, 1 page) | Commercial | P1 | CEO | 4h | $0 | None | [x] Done | Day 21
SI-001 | Document data handling policy (1 page) | Security | P1 | CEO | 4h | $0 | None | [ ] Pending | Day 21
SI-002 | Confirm no pharma data stored in LLM training pipeline | Security | P1 | Engineering | 4h | $0 | None | [ ] Pending | Day 14
SI-003 | Document pilot data isolation protocol | Security | P1 | Engineering | 6h | $0 | None | [ ] Pending | Day 21
SI-004 | Commission penetration test (basic, external) | Security | P2 | CEO | 2h | $3–8K | None | [ ] Pending | Day 28
SI-005 | Begin SOC 2 Type I process | Security | P3 | CEO | 4h | $15–30K | None | [ ] Pending | Post-pilot
WB-001 | Add /pharma page with torcetrapib case hero | Website | P1 | Engineering | 8h | $0 | CA-001, GD-001 | [ ] Pending | Day 21
WB-002 | Add torcetrapib case card to homepage | Website | P1 | Engineering | 4h | $0 | WB-001 | [ ] Pending | Day 21
WB-003 | Add GitHub link to website footer | Website | P1 | Engineering | 1h | $0 | MP-001 | [ ] Pending | Day 14
WB-004 | Add LLM limitation disclosure to website | Website | P1 | Engineering | 2h | $0 | GD-001 | [ ] Pending | Day 14
WB-005 | SEO metadata for /pharma page | Website | P2 | Engineering | 2h | $0 | WB-001 | [ ] Pending | Day 24
VL-001 | Identify independent expert reviewer (1 person, torcetrapib) | Validation | P1 | CEO | 4h | $0 | None | [ ] Pending | Day 14
VL-002 | Brief independent reviewer and agree scope | Validation | P1 | CEO | 2h | $0 | VL-001 | [ ] Pending | Day 18
VL-003 | Independent review of torcetrapib case | Validation | P2 | Reviewer | 16h | $3–8K | VL-002 | [ ] Pending | Day 45
VL-004 | Incorporate reviewer feedback into case report | Validation | P2 | Research Lead | 8h | $0 | VL-003 | [ ] Pending | Day 50

## Critical Path
Task ID | Description | Classification | Due Date | Hours | Cost | Blocker If Missing
GD-006 | Freeze Pharma Constitution v1 | MUST HAVE | Day 1 | 1h | $0 | First outreach lacks governance credibility
LC-001 | Engage legal counsel | MUST HAVE | Day 1 | 2h | $9–23K | No legal templates = no pilot discussions
GD-001 | LLM contamination disclosure (LDS-001) | MUST HAVE | Day 3 | 4h | $0 | Every email is vulnerable to 'you knew the answer'
GD-002 | Case selection bias disclosure (CSDS-001) | MUST HAVE | Day 3 | 3h | $0 | Expert reviewer kills credibility in first meeting
GD-003 | Evidence boundary statement (EBS-001) | MUST HAVE | Day 3 | 4h | $0 | No verifiable evidence boundary = no credibility
GD-005 | Verubecestat PC-011 contextualisation | MUST HAVE | Day 3 | 2h | $0 | Failure case unexplained = trust destroyed
GD-004 | Add disclosures to all 10 case reports | MUST HAVE | Day 5 | 6h | $0 | External documents lack required disclosures
MP-001 | Create GitHub repository | MUST HAVE | Day 7 | 4h | $0 | No public methodology = no credibility
MP-002 | README.md | MUST HAVE | Day 10 | 6h | $0 | GitHub without README is worse than no GitHub
MP-003 | Publish constitution | MUST HAVE | Day 10 | 2h | $0 | Methodology claim without published constitution
MP-004 | Publish persona definitions | MUST HAVE | Day 10 | 3h | $0 | '10 personas' is unverifiable without this
MP-005 | Publish LIMITATIONS.md | MUST HAVE | Day 10 | 3h | $0 | Hiding limitations destroys trust when discovered
MP-006 | Publish torcetrapib case (public) | MUST HAVE | Day 13 | 4h | $0 | No public case = no credibility for email claim
LC-002 | Pilot agreement template (PAT-001) | MUST HAVE | Day 20 | 16h | Included | Cannot discuss pilot terms without template
LC-003 | DPA template (DPAT-001) | MUST HAVE | Day 20 | 12h | $3–8K | Any pharma company will ask about data handling
CA-001 | Methodology one-pager | MUST HAVE | Day 18 | 6h | $0–2K | Email 1 has no attachment without this
CA-002 | CRO partnership one-pager | MUST HAVE | Day 18 | 4h | $0–2K | CRO Email 1 has no attachment without this
CA-008 | Personalise Email 1 for 5 targets | MUST HAVE | Day 28 | 3h | $0 | Cannot send Day 29 emails
CA-009 | Populate CRM workbook | MUST HAVE | Day 28 | 2h | $0 | No tracking = no follow-up discipline
GD-007 | Pre-specify Cases 11–20 | SHOULD HAVE | Day 14 | 6h | $0 | Selection bias objection cannot be fully answered
GD-008 | Evidence manifests (all 10 cases) | SHOULD HAVE | Day 21 | 40h | $0 | Evidence boundary not fully verifiable
CA-007 | Validation library summary (2 pages) | SHOULD HAVE | Day 18 | 4h | $0 | No summary document for follow-up emails
CA-003 | Redesigned torcetrapib IPR (6 pages) | SHOULD HAVE | Day 21 | 8h | $0 | Existing IPR lacks external formatting
CA-004 | Demo slide deck (6 slides) | SHOULD HAVE | Day 21 | 8h | $0–2K | Demo relies on verbal description only
CA-005 | Sofosbuvir case summary (1 page) | SHOULD HAVE | Day 21 | 4h | $0 | Follow-up Email 2 has no attachment
CA-006 | Pilot proposal template (1 page) | SHOULD HAVE | Day 22 | 4h | $0 | Cannot formalise pilot discussion
SI-001 | Data handling policy | SHOULD HAVE | Day 21 | 4h | $0 | IQVIA and large pharma will ask immediately
WB-001 | Website /pharma page | SHOULD HAVE | Day 21 | 8h | $0 | No public case page for email recipients to visit
VL-001 | Identify independent reviewer | SHOULD HAVE | Day 14 | 4h | $0 | Independent validation not in progress
SI-004 | Penetration test | NICE TO HAVE | Day 28 | 2h | $3–8K | Security objection cannot be answered with evidence
LC-007 | Professional indemnity insurance | NICE TO HAVE | Day 28 | 4h | $2–8K/yr | Procurement teams will ask
VL-003 | Independent review (torcetrapib) | NICE TO HAVE | Day 45 | 16h | $3–8K | Credibility boost but not required for first meeting
MP-011 | Reproducibility test | NICE TO HAVE | Day 28 | 8h | $0 | Strengthens methodology claim
WB-005 | SEO metadata | NICE TO HAVE | Day 24 | 2h | $0 | Not relevant before first outreach

## Asset Tracker
Asset | File Name | Status | External? | Needs Revision | Revision Required
Torcetrapib IPR (4 pages) | torcetrapib-institutional-proof-report-2026.pdf | ✅ Exists | Yes | YES | Add LLM disclosure to Page 1 (prominent, boxed)
Torcetrapib case summary (1 page) | torcetrapib-case-study-summary.pdf | ✅ Exists | Yes | YES | Add LLM disclosure
Torcetrapib council JSON | torcetrapib-council-result.json | ✅ Exists | Internal | No | None
Torcetrapib flagship one-pager | torcetrapib-flagship-one-pager.pdf | ✅ Exists | Yes | No | None
Cases 2–10 case reports (9 PDFs) | cases/case02–10.pdf | ✅ Exists | Internal | YES | Add LLM disclosure to each
Cumulative library update | pharma-validation-library-cumulative-update.pdf | ✅ Exists | Internal | YES | Add LLM disclosure
Flagship case package | pharma-flagship-case-package.pdf | ✅ Exists | Internal | No | None
Institutional proof package | pharma-institutional-proof-package-v1.pdf | ✅ Exists | Internal | No | None
Market entry plan | pharma-market-entry-plan.pdf | ✅ Exists | Internal | No | None
Launch readiness audit | pharma-launch-readiness-audit.pdf | ✅ Exists | Internal | No | None
28-day credibility sprint | pharma-credibility-sprint-28day.pdf | ✅ Exists | Internal | No | None
Pilot demo specification | pharma-pilot-demo-specification.pdf | ✅ Exists | Internal | No | None
Outreach engine | pharma-outreach-engine.pdf | ✅ Exists | Internal | No | None
CRM workbook | AgenThink-Pharma-CRM-v1.xlsx | ✅ Exists | Internal | YES | Populate Day-29 contacts (CA-009)
Evidence boundary architecture | pharma-evidence-boundary-architecture.pdf | ✅ Exists | Internal | No | None
Red team review | pharma-validation-library-red-team-review.pdf | ✅ Exists | Internal | No | None
Pharma case research data | pharma_case_research.json | ✅ Exists | Internal | No | None
Contact research data | pharma_contact_research.json | ✅ Exists | Internal | No | None
LLM contamination disclosure (LDS-001) | LDS-001.pdf | ❌ Missing | Yes | — | Create: GD-001 (Day 3)
Case selection bias disclosure (CSDS-001) | CSDS-001.pdf | ❌ Missing | Yes | — | Create: GD-002 (Day 3)
Evidence boundary statement (EBS-001) | EBS-001.pdf | ❌ Missing | Yes | — | Create: GD-003 (Day 3)
Methodology one-pager | methodology-one-pager.pdf | ❌ Missing | Yes | — | Create: CA-001 (Day 18)
CRO partnership one-pager | cro-partnership-one-pager.pdf | ❌ Missing | Yes | — | Create: CA-002 (Day 18)
Pilot agreement template (PAT-001) | PAT-001.pdf | ❌ Missing | Yes | — | Create: LC-002 (Day 20)
DPA template (DPAT-001) | DPAT-001.pdf | ❌ Missing | Yes | — | Create: LC-003 (Day 20)
GitHub repository | github.com/agenthinkmesh/pharma-council-v1 | ❌ Missing | Yes | — | Create: MP-001–006 (Day 7–13)
Demo slide deck (6 slides) | torcetrapib-demo-deck.pptx | ❌ Missing | Yes | — | Create: CA-004 (Day 21)
Redesigned torcetrapib IPR (6 pages) | torcetrapib-ipr-v2.pdf | ❌ Missing | Yes | — | Create: CA-003 (Day 21)
Sofosbuvir case summary (1 page) | sofosbuvir-case-summary.pdf | ❌ Missing | Yes | — | Create: CA-005 (Day 21)
Pilot proposal template (1 page) | pilot-proposal-template.pdf | ❌ Missing | Yes | — | Create: CA-006 (Day 22)
Validation library summary (2 pages) | validation-library-summary.pdf | ❌ Missing | Yes | — | Create: CA-007 (Day 18)

## CEO Weekly Plan
Day | Date | Priority | Action | Hours | Output | Task IDs
1 | Jun 15 | P0 | Engage legal counsel — send brief with scope | 2h | Legal engagement confirmed | LC-001
1 | Jun 15 | P0 | Freeze Pharma Constitution v1 — write dated note | 1h | Constitution frozen | GD-006
2 | Jun 16 | P0 | Write LLM contamination disclosure (LDS-001) | 4h | LDS-001 draft | GD-001
3 | Jun 17 | P0 | Write case selection bias disclosure (CSDS-001) | 3h | CSDS-001 draft | GD-002
3 | Jun 17 | P0 | Write evidence boundary statement (EBS-001) | 4h | EBS-001 draft | GD-003
3 | Jun 17 | P0 | Write verubecestat PC-011 contextualisation | 2h | Note added to case 6 | GD-005
4 | Jun 18 | P0 | Add all disclosures to all 10 case reports | 6h | 10 updated case reports | GD-004
5 | Jun 19 | P0 | Create GitHub repository + add LICENSE | 4h | Repo created | MP-001, MP-010
5 | Jun 19 | P1 | Write README.md draft | 3h | README draft | MP-002
8 | Jun 22 | P0 | Finalise README.md + publish constitution | 4h | README + constitution live | MP-002, MP-003
8 | Jun 22 | P0 | Publish persona definitions | 3h | personas.md live | MP-004
9 | Jun 23 | P0 | Publish LIMITATIONS.md | 3h | LIMITATIONS.md live | MP-005
9 | Jun 23 | P1 | Publish evidence manifest schema + scoring rubric | 4h | 2 files live | MP-007, MP-008
10 | Jun 24 | P0 | Publish torcetrapib case summary (public version) | 4h | Case live on GitHub | MP-006
10 | Jun 24 | P1 | Add CITATION.cff | 1h | Citation file live | MP-009
11 | Jun 25 | P1 | Write validation library summary (2 pages) | 4h | CA-007 draft | CA-007
11 | Jun 25 | P1 | Identify independent expert reviewer | 4h | Reviewer identified | VL-001
12 | Jun 26 | P1 | Pre-specify Cases 11–20 selection criteria | 6h | GD-007 published on GitHub | GD-007
12 | Jun 26 | P1 | Add GitHub link + LLM disclosure to website | 3h | Website updated | WB-003, WB-004
15 | Jun 29 | P0 | Write methodology one-pager (1 page, PDF) | 6h | CA-001 final | CA-001
16 | Jun 30 | P0 | Write CRO partnership one-pager (1 page, PDF) | 4h | CA-002 final | CA-002
16 | Jun 30 | P1 | Brief independent reviewer — agree scope | 2h | Reviewer briefed | VL-002
17 | Jul 1 | P1 | Write validation library summary (2 pages) | 4h | CA-007 final | CA-007
17 | Jul 1 | P1 | Assign case IDs and version numbers | 2h | All cases versioned | GD-009
18 | Jul 2 | P1 | Redesign torcetrapib IPR (6 pages, external) | 8h | CA-003 final | CA-003
19 | Jul 3 | P1 | Create demo slide deck (6 slides) | 8h | CA-004 final | CA-004
19 | Jul 3 | P1 | Write sofosbuvir case summary (1 page) | 4h | CA-005 final | CA-005
20 | Jul 4 | P0 | Review legal drafts (PAT-001, DPAT-001) | 4h | Legal templates approved | LC-002, LC-003
20 | Jul 4 | P1 | Write pilot proposal template (1 page) | 4h | CA-006 final | CA-006
20 | Jul 4 | P1 | Document data handling policy | 4h | SI-001 final | SI-001
22 | Jul 6 | P1 | Build /pharma page on website | 8h | Website /pharma live | WB-001
22 | Jul 6 | P1 | Add torcetrapib case card to homepage | 4h | Homepage updated | WB-002
23 | Jul 7 | P1 | Write evidence manifests Cases 1–5 | 20h | 5 manifests complete | GD-008
24 | Jul 8 | P1 | Write evidence manifests Cases 6–10 | 20h | All 10 manifests complete | GD-008
25 | Jul 9 | P0 | Personalise Email 1 for all 5 Day-29 targets | 5h | 5 emails ready to send | CA-008
26 | Jul 10 | P0 | Populate CRM workbook — all 5 Day-29 contacts | 2h | CRM ready | CA-009
26 | Jul 10 | P0 | Final review of all P0 assets | 2h | P0 checklist complete | All P0
27 | Jul 11 | P0 | CEO review of all 5 Email 1 drafts | 2h | Emails approved | CA-008
28 | Jul 12 | P0 | Confirm legal templates received and approved | 2h | Legal package complete | LC-002, LC-003
29 | Jul 13 | P0 | SEND: Email 1 to Recursion (09:00) | 0.5h | Email sent | Day 29
29 | Jul 13 | P0 | SEND: Email 1 to Insilico (10:30) | 0.5h | Email sent | Day 29
29 | Jul 13 | P0 | SEND: Email 1 to Exscientia (12:00) | 0.5h | Email sent | Day 29
29 | Jul 13 | P0 | SEND: Email 1 to Relay (14:00) | 0.5h | Email sent | Day 29
29 | Jul 13 | P0 | SEND: Email 1 to Medpace (16:00) | 0.5h | Email sent | Day 29

## Outreach Readiness
Target | Ready Today? | Blocking Items | Contact | Sequence | Earliest Date | Pilot Probability
Recursion | NO | GD-001, GD-002, LC-002, MP-001–006, CA-001 | Chris Gibson (CEO) | Biotech | Day 29 (Jul 13) | 40–55%
Insilico Medicine | NO | GD-001, GD-002, LC-002, MP-001–006, CA-001 | Alex Zhavoronkov (CEO) | Biotech | Day 29 (Jul 13) | 35–50%
Exscientia | NO | GD-001, GD-002, LC-002, MP-001–006, CA-001 | Andrew Hopkins (CEO) | Biotech | Day 29 (Jul 13) | 30–45%
Relay Therapeutics | NO | GD-001, GD-002, LC-002, MP-001–006, CA-001 | CMO (LinkedIn) | Biotech | Day 29 (Jul 13) | 25–40%
Medpace | NO | GD-001, GD-002, LC-002, MP-001–006, CA-002 | CMO (LinkedIn) | CRO | Day 36 (Jul 20) | 35–50%
ICON plc | NO | GD-001, GD-002, LC-002, MP-001–006, CA-002 | Dr. Brendan Buckley (CMO) | CRO | Day 36 (Jul 20) | 25–40%
IQVIA | NO | All P0 + SI-001 (data handling policy) | AI/Digital lead (LinkedIn) | Large Pharma | Day 44 (Jul 28) | 20–30%
Roche | NO | All P0 + P1 + first pilot complete | CMO (LinkedIn) | Large Pharma | Post-pilot | 10–20%
Novartis | NO | All P0 + P1 + first pilot complete | Shreeram Aradhye (CMO) | Large Pharma | Post-pilot | 10–20%
Pfizer | NO | All P0 + P1 + first pilot complete | CMO (LinkedIn) | Large Pharma | Post-pilot | 8–15%

## Stop Doing List
Activity | Why Stop | What To Do Instead | Severity
Writing new strategy documents | 9 strategy documents already exist. None close a P0 blocker. | Close GD-001 (LLM disclosure) today | CRITICAL
Expanding case library beyond Case 10 | Cases 11–50 not needed before first outreach | Write GD-007 (pre-specification) and stop | HIGH
Researching additional pharma targets | 25 targets already identified; 5 ready for Day 29 | Personalise the 5 Day-29 emails | HIGH
Building new market analyses | Market entry plan, IPP, and audit are complete | Engage legal counsel (LC-001) today | HIGH
Refining outreach sequences | 3 complete sequences already exist | Personalise existing sequences for specific contacts | HIGH
Creating new scoring frameworks | OVS, proof score, readiness dashboard are complete | Publish existing methodology on GitHub (MP-001) | HIGH
Researching competitor AI governance tools | Competitive analysis is not a P0 blocker | Build the GitHub repository | MEDIUM
Writing new constitutional rules | Constitution is frozen (GD-006) | Respect the freeze | HIGH
Producing additional case summaries | Torcetrapib + sofosbuvir sufficient for Day 29 | Write methodology one-pager (CA-001) | MEDIUM
Creating new financial models | Revenue model is complete in market entry plan | Close the legal package (LC-001) | MEDIUM
Designing new demo environments | Demo specification is complete | Build the 6-slide demo deck (CA-004) | MEDIUM
Producing additional red team reviews | One red team review is sufficient; findings documented | Act on the findings | HIGH
Writing new objection playbooks | 50 objections already documented | Memorise the top 10 | LOW
Researching pharma industry trends | Not required before first outreach | Send the emails | LOW
Building new tracking systems | CRM workbook is complete | Populate it (CA-009) | MEDIUM